## Req Traceability Matrix
REQUIREMENTS TRACEABILITY MATRIX
| Project Name: | Medicine Supply Map
Project Code:
| Revision: | 0.1
| Date: | 2021-08-31
Accountable | Product Manager |  |  | Project Manager |  |  |  | PROJECT MANAGER |  | PRODUCT OWNER
ID | Marketing Requirement Baseline | Acceptance Criteria | Priority | Comments | System | Quality | Software | Verification Method | Link to test results | Results Status | Date
MR000 | The solution shall indicate both active and inactive manufacturing locations of APIs and FDFs | A table with API name, FDF name, country of FDF manufacture, city of FDF manufacture, name of FDF manufacturing org, country of API manufacture, city of API manufacture, name of API manufacturing org, and column indicating active/inactive | high | Can we make this separate tables? FDF would include NDCs. I think linkages should only be presented on the Maps and Scenerio Planning tab. Otherwise it's too crowded.
MR001 | The solution should visualize the active and inactive manufacturing locations of APIs and FDFs | A world map with different markers for: - Active FDF manufacturer - Active API manufacturer - Inactive FDF manufacturer - Inactive API manufacturer Each marker shall be placed on the map over the city of manufacture if known. If unknown, the marker shall be placed over the center of the country. The map shall display all FDFs and APIs in the current analysis. | medium | can't list active/inactive due to ECIC
MR002 | The solution shall indicate any supply chain relationships between API and FDF manufacturers where known | The table (MR000) can have multiple entries for a single FDF with multiple API suppliers. The world map should show linkages between API suppliers to FDF manufacturers | high | Not sure how to display
MR003 | The solution shall identify APIs and FDFs at the greatest risk of shortage and quantify the risk | A column in the table (MR000) with a total risk score (% risk of shortage) | high | % risk of shortage, not approved language
MR004 | The solution shall identify and quantify all known supply shortage risk factors for APIs and FDFs | A column in the table (MR000) for each risk factor with risk factor scores (% increase or decrease in risk of shortage) | high | We don't have an API shortage model
MR005 | The solution shall allow the user to rank APIs and FDFs by total drug shortage risk and/or by individual risk factors | Sort by column high to low or low to high | high | We don't have an API shortage model
MR006 | The solution shall visualize the shortage risk and risk factor contributions to shortage risk for individual APIs and FDFs | When a FDF or API is selected, a waterfall plot shows the % increase or decrease in risk of shortage for each risk factor and the total % risk of shortage | high | We don't have an API shortage model
MR007 | The solution should visualize the shortage risk and risk factor contributions to shortage risk for groups of APIs and/or FDFs | A waterfall plot which shows the % increase or decrease in risk of shortage for each risk factor and the total % risk of shortage for all APIs and FDFs currently included in an analysis | medium | We don't have an API shortage model
MR008 | The solution shall allow the user to add or remove APIs and FDFs to or from their analysis based on: drug class, essential/non-essential medicines, country of origin, finished dosage form, manufacturing organization, recent quality event, and other information as available | A column in the table (MR000) for each of: drug class, essential/non-essential medicines, country of origin, finished dosage form, manufacturing organization, recent quality event, and other information as available User can filter on any number of columns to remove drugs from the analysis | high | Need to build "recent quality event" and essenitalness
MR009 | The solution shall indicate APIs and FDFs that are actively in shortage and provide information on the duration of the shortage | Columns in the table (MR000) for in shortage (Yes/No), start of shortage date, days in shortage It would be cool to highlight the row in red for APIs and FDFs currently in shortage. It would be cool to have a list on a separate page of all the drugs in shortage | high
MR010 | The solution should indicate API and FDF manufacturers who have experienced a quality event (i.e. FDA warning letter) in a given time period | A separate list/table with columns for API name, FDF name, country of FDF manufacture, city of FDF manufacture, name of FDF manufacturing org, country of API manufacture, city of API manufacture, name of API manufacturing org, type of quality event, date of quality event User should be able to input start and end date and the table should populate with all entries within that time period. By default the time period will be the past 12 months from the current date | low
MR011 | The solution shall recalculate/update only with affirmative user input | A button labeled "Update" shall be visible to the user. The user must press that button to force update the table/results. | high
MR012 | The solution shall recalculate/update in less than 5 seconds | After the "Update" button has been pressed, the results, including visualizations, shall be populated within 5 seconds | high
MR013 | The solution shall allow the user to have multiple analyses open simultaneously | The user can open multiple tabs. All analysis open in a new tab. | high
MR014 | The solution shall allow the user to create an analysis report | The user shall be able to export/save the table/analysis in .CSV file format. The user shall be able to copy/paste visualizations into Microsoft Office applications | high
MR015 | The solution shall maintain user settings from one session to the next | Filters, dates, visible columns shall be the same when the user closes and reopens the solution or creates a new tab | high
MR016 | The solution shall allow a user to save, open, and re-use queries/analyses | Save a set of filters, dates, and visible columns as a query. Open a query in an analysis to apply those settings to the new analysis. Save an analysis and reopen it later to re-run with updated data. | high
MR017 | The solution should update with new data when source data is updated | The solution should connect to master databases. The solution should compare data to the master databases and update if there are any differences. A user should not be interrupted by this update. | medium
MR018 | The solution shall allow a user to hide/unhide information | Hide/unhide columns in the table | high
MR019
MR020
MR021
MR022
MR023
MR024

## Technical Requirements
Technical Requirements Document
Projects in this list may be active or in the backlog. The intent is to capture all items … big and small.
Open source skelton (without real data) located here: https://analyticalmeanderings.github.io/
ID | JiraStory | Description | Status
1 |  | Seven interactive tabs across the top of the screen, enabled with MERN (MongoDB, NodeJS, ReactJS, ExpressJS). MongoDB is lowest priority as it can be replaced with AWS (assumption needs validation).
2 |  | On the home tab, a dynamically updated Top 10 At Risk FDF Products list. Pulled from AWS.
3 |  | On the home tab, dynamically pulled API calls with news alerts related to the pharma industry
4 |  | On the home tab, a tutorial video. | BLOCKED: Business to create video
5 |  | On the Upstream Info tab, a dynamically updated table that lists all API manufacterers, API products, City, Country, Relevent Application Data, Activeness Flag, and Forecasted Volume. Ability to filter and sort each column. Pulled from AWS.
6 |  | On the Downstream Info tab, a dynamically updated table that lists all API manufacterers, API products, City, Country, Relevent Application Data, Activeness Flag, Forecasted Volume, and NDC Codes. Ability to filter and sort each column. Pulled from AWS.
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22

## Change Management
REQUIREMENTS CHANGE MANAGEMENT
Owner | Project Manager
Date:
ID | Change Description | Originator | Reason | Phase entered | Date entered | Evaluator | Decision | Date closed | Included in Rev#
CR001
CR002
CR003
CR004
CR005
CR006
CR007
CR008
CR009
CR010
CR011
CR012
CR013
CR014
CR015
CR016
CR017
CR018
CR019
CR020